## Sheet1
Week | Project Goals | Notes | What Is Needed
1 (1/21/24 - 1/27/24) | Literature review on AR/MR technologies in manufacturing | Will have to use open source renders, may reach out to companies later in process | Esp32
| Select objects and renders for object detection | Importing models in Blender | Raspberry Pi 4
| Begin developing training generator pipeline | Python for rendering automation | Raspberry Pi 5
|  | FreeCAD for converting .SLDPRT and .STEP files to .obj, .stl (blender compatible) | Arduino Uno
MSI X370 Gaming Pro Carbon Motherboard
Logitech G27 wheel
2 (1/28/24 - 2/3/24) | Finish developing training generator output
Begin working on object detection model
3 (2/4/24 - 2/10/24) | Continue working on object detection, classification, tracking
Test and record results of model
3D tracking model over actual object (Image Segmentation)
4 (2/11/24 - 2/17/24) | Begin developing AR remote assistance platform
5 (2/18/24 - 2/24/24) | AR remote assistance development
6 (2/25/24 - 3/2/24) | AR remote assistance development
7 (3/3/24 - 3/9/24) | AR remote assistance development
8 (3/10/24 - 3/16/24) | Preliminary testing and feedback
Implement object detection model in AR remote assistance platform
9 (3/17/24 - 3/23/24) | AR remote assistance development
10 (3/24/24 - 3/30/24) | AR remote assistance development
First round of testing
Begin VR implementation
11 (3/31/24 - 4/6/24) | AR remote assistance development
12 (4/7/24 - 4/13/24) | AR remote assistance development
13 (4/14/24 - 4/20/24) | AR remote assistance development
14 (4/21/24 - 4/27/24) | Second round of testing and refinement
15 (4/28/24 - 5/3/24) | Final evaluation and preparation for thesis defense
16 (5/4/24 - 5/11/24) | Thesis defense and live demo